## Gantt Chart
Student Name |  | Prakash Shrestha
Student ID |  | 10622983
Supervisor |  | Hamidreza Khaleghzadeh
Proposed Thesis Title |  | Exploring the Impact of Location and Property Attributes on Housing Prices in Perth: A Comprehensive Analysis
S.N | TASK |  | Project Timeline
|  |  | JUNE |  |  |  | JULY |  |  |  | AUGUST
|  |  | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk6 | Wk7 | Wk8 | Wk9 | Wk10 | Wk11 | Wk12
1 | Research proposal emailed to supervisor | bar: JUNE Wk1
2 | Define Research Topic | bar: JUNE Wk1
3 | Write Literature review | bar: JUNE Wk2 to JUNE Wk4
4 | Supervisor's feedback on literature review | [13 empty] | Symbols | bar: JULY Wk5
5 | Write Methodology | [14 empty] | Expected time frame on task | bar: JULY Wk6 to JULY Wk7
6 | Supervisor's feedback on Research Methodology | [13 empty] | M | Milestone | bar: JULY Wk7
7 | Data Collection | [13 empty] | C | Submission | bar: JULY Wk8
8 | Data Preprocessing | bar: JULY Wk8
9 | Feature Selection | bar: JULY Wk8
10 | Develop Mechine learning Model | bar: JULY Wk8 to AUGUST Wk9
11 | Hyperparameter Tuning | bar: AUGUST Wk9
12 | Evaluation Models | bar: AUGUST Wk9
13 | Interpret Results | bar: AUGUST Wk9
14 | Thesis review by supervisors | bar: AUGUST Wk10
15 | Thesis writing/editing | bar: AUGUST Wk10
16 | Revised Thesis | bar: AUGUST Wk11
17 | Finalized Thesis | bar: AUGUST Wk11
18 | Submit Thesis | bar: AUGUST Wk12
19 | Prepation of Powerpoint Presentation | bar: AUGUST Wk11
S.N. | Milestones
1 | Completion of Literature Review | bar: JULY Wk5
2 | Completion of Methodology | bar: JULY Wk7
3 | Completion of Machine learning Model | bar: AUGUST Wk9
4 | Model Evaluation | bar: AUGUST Wk9
5 | Thesis Finalization | bar: AUGUST Wk11
6 | Thesis Submisson | bar: AUGUST Wk12